GelatoConnect MIS - Development Roadmap

Release date: May 1, 2026

1. Context & Objective

11 customers have already signed up for the MIS, and the 2026 plan targets 70 MIS customers. To deliver on this, we are extending GelatoConnect from an estimation tool and web-to-print orders - into a complete Management Information System - the operating system for a PSP's entire business.

This requires a fundamental shift. We are moving from a system designed around SKU-based, catalog-driven web-to-print production to one that supports job-based work - where every job is unique, every product is configured dynamically at quote time, and the system must handle 100% of what a PSP can produce. Every part of the platform - from order intake to invoicing - must become flexible enough to support any job that walks through the door.

Our competitive advantage: we already have strong automation (AI-powered estimation, automated workflows). What we need to build now are the order qualifiers for job-based work - the core capabilities without which a PSP cannot adopt the system as their primary MIS.

2. Workstream Overview

The MIS build is organized into four parallel workstreams, each covering a distinct phase of the PSP workflow.

Phase 1 - Core MIS (Target: May 1, 2026)

| Stream | Scope | Owner (PM) |
| --- | --- | --- |
| WS1 | Pre-Order Workflow: Quote-to-Order, Post-Conversion Order Editing, Job Ticketing, File Receipt & Proofing, Reprints, Customer communication triggers | Styrbjorn |
| WS2 | Production Tracking, Station Views, Outsourcing | Felix |
| WS3a | Shipping & Fulfillment: Pallet/freight shipping (manual), multi-address orders | Kian |
| WS3b | Inventory & Procurement: Inventory allocation on order conversion, stock management | Vipul |
| WS4 | Finance: Invoicing, Customer CRM, ERP Integration (QuickBooks, Dynamics, Sage) | Kirill |

Phase 2 - Advanced (Post May 1, 2026)

| Stream | Scope | Owner (PM) |
| --- | --- | --- |
| WS1 | Customer Portal | Styrbjorn |
| WS2a | AI Scheduling | Felix |
| WS2b | Automated Imposition (incl external integrations) and Workflow | Nilesh |
| WS3a | Automated Carrier Integrations incl freight | Kian |
| WS3b | Advanced Inventory Features, supplier integrations | Vipul |
| WS4 | Analytics & P/L | Kirill |

3. Delivery Timeline

All teams follow the same cadence: discovery first, then weekly build-and-deliver sprints, culminating in a customer-facing release on April 17 and final release on May 1.

| Date | Milestone | Deliverable |
| --- | --- | --- |
| 20 Mar | Kickoff with teams; incl all PMs and tech leads | Team alignment |
| 24 Mar | Scope/tickets defined, and week-by-week delivery plan presented by each workstream | Scope + plans |
| 27 Mar | Sprint 1 deliverables - foundations in place per workstream and scope refined based on initial iterations | Foundational build |
| 3 Apr | Sprint 2 deliverables - first functional builds per workstream | Working builds |
| 10 Apr | Sprint 3 deliverables - core features completed | Feature complete |
| 17 Apr | MIS v1.0 - first customer-facing deployment; begin pilot field testing | Customer release |
| 17 Apr - 1 May | Pilot deployment in controlled environment; field testing with pilot customers; collect feedback and iterate | Testing & feedback |
| 24 Apr | Updates based on customer feedback; validation and refinement | Refined release |
| 1 May | MIS Full Release - production-ready to rollout to customers | Go-live |

4. Leadership & Ownership

Discovery Phase Lead: Pradeep - will lead the kickoff and support each PM through the discovery phase to create their workstream plans.

Overall Tech Lead: Paul Colleoni - single technical point of contact across all workstreams. Vitali Tkachov has created the MIS architecture proposal and will support, but Paul will lead its execution across tech teams.

Delivery Owner: Each PM is responsible for keeping their deliverables on track and ensuring delivery timelines are met.

5. Pilot Customers

We propose engaging two pilot customers to co-develop and validate the MIS, replicating the approach that worked successfully with Programmatic and ESP two years ago:

- PrintEvolved (Metric/EU) - Technical founder (Liam) who has built his own MIS; deep, practical understanding of print operations; recently signed up for the MIS; strong ability to guide product development.

- Hudson (Imperial/US) - Established US-based PSP; Chad is an engaged contact who understands print workflows; provides Imperial/US market perspective to complement PrintEvolved's EU view.

These two customers give us one metric and one imperial setup, covering both configuration paradigms. They were selected based on their technical depth, willingness to collaborate, and their profile as representative ICP customers.

6. Why This Takes What It Takes

This is not a feature addition - it is a platform transformation. We are fundamentally changing how GelatoConnect works, from a system designed to sell products (e-commerce mindset) to a system designed to produce them (manufacturing mindset). Specifically:

- Unifying data models: AI Estimator and GelatoConnect currently maintain separate definitions for machines, inventory, and products. These must become a single source of truth for the MIS to function.

- Flexibility as the order qualifier: Unlike web-to-print, an MIS must support anything a PSP can produce - including outsourced work, custom finishing, and manual processes. Each step of the chain must be able to handle 100% of a PSP's job mix.

- Cross-functional by nature: The MIS touches every product area - order intake, workflow, imposition, logistics, and finance. This is why four workstreams with dedicated PMs are needed rather than a single team.

- Market validation: The #1 reason PSPs hesitate to adopt a new MIS is the heavy implementation lift (typically 6-12 months). Our target is core workflow go-live in under one week - validated with real pilot customers, not theoretical.

7. References

For detailed workstream breakdowns, technical architecture, and prototype walkthrough:

- MIS Prototype Walkthrough (Loom) - Video demo of the MIS prototype and key user flows: [link]

- GelatoConnect MIS Phase 1: Development Plan - Detailed workstream PRDs, capability breakdowns, and requirements: [link]

- MIS System Architecture Proposal - Engineering architecture, data model, and integration plan: [link]